## HOW TO USE
Wind Energy Decomissioning Calculator
Terms of use and disclaimer
This calculator is provided for use by the public including persons engaging in commercial activities.
No person or entity (including, without limitation, the State of New South Wales) associated with the development of the calculator makes any representation or warranty regarding its contents, or is liable for any loss or damage whatsoever that may result from the use of the template or any portion or variation thereof, or any other materials presented in conjunction with the calculator, or any errors or omissions in its contents.
Users of the calculator must exercise their own skill and judgment and should seek advice from a suitably qualified experts, where appropriate.
The outputs of the calculator are estimations only and subject to a range of variables that can and will change overtime.
How to use
This calculator contains a range of fields that can be modified to account for the individual aspects of a project. Other fields and information are locked to provide consistent estimations. Enter information into the 'CALCULATOR TAB' to determine an estimate.
Fields that can be modified are shown in blue

## CALCULATOR
WIND TURBINE DECOMMISSION INPUTS |  |  |  |  | WIND TURBINE TRIGER
SECTION | DESCRIPTION | UNIT | QUANTITY | COMMENT | DESCRIPTION | TRIGGER
| Overall Project Size | MW | 270 | Insert Total Mega Watts for Project | Haul Road Removal | No | 0
Tower | Number of Towers | each | 75 |  | Underground Cable/Pit Removal | No | 0
| Tower Height | m | 137 | This is one function of main crane size | Concrete Foundation Removal | No | 0
| Tower Weight | tonne | 810 |  | Steel and Iron Recovery | Yes | 1
| Average Turbine Size | MW/turbine | 3.6 |  | Aluminium and Alloy Recovery | Yes | 1
| Nacelle Weight Per Turbine Size | tonne/MW | 56 | This is onether function of main crane size | Copper and Alloy Recovery | Yes | 1
| Blade Weight Per Tower | tonne | 26 |  | Polymer Recovery | Yes | 1
| Surface area of foundation above ground | m2 | 30 | Plan area of foundation above existing ground | Carbon/Glass Recovery | Yes | 1
| Height of Foundation above Existing ground | m | 2.5 |  | Electronics Recovery | Yes | 1
| Depth of Foundation Below Ground To Be Removed | m | 1 |  | Fuels/Fluids Recovery | Yes | 1
| Oil/Grease Quantity | lt | 45600 | per turbine | Concrete Recovery | Yes | 1
Cable/Pits | Number of Cables On Towers | each | 3 | Assumed 3 sets of cables and the length is tower length plus 25m
| Number of Cables/Conduits Below Ground | each | 6 | Refer to 'Wind Turbine Triger' table to exclude
| Average Copper mass kg Per KM | kgs/km | 2.298
| Pit Intervals | m | 250
Access Road/Make Good | Access Road Quantity | m2 | 202500
| Access Road Base Depth | m | 0.15
| Topsoiling/Hydroseeding | m2 | 25750 | Potentially for removed access road, removed buildings and removed turbines
Demolish | Number of Buildings To Be Demolished | each | 3
Site Size | Overall Site Size | Ha | 1000000
Mod/Demob | Number of Plants To Mobilise | each | 14
| Crew Size | each | 53
Recovery | Steel & iron Recovery | % | 88
| Aluminium and Alloy Recovery | % | 1
| Copper and Alloy Recovery | % | 0.6
| Polymer Recovery | % | 4
| Carbon/Glass Recovery | % | 5
| Electronics Recovery | % | 0.6
| Fuels/Fluids Recovery | % | 0.6
Distances | Avg. Distance Between Turbines | m | 500 | This will affect the productivity, productivity will be less since the inefficiency increases
| Distance to Scrap/Recycle | km | 200 | This will affect the cost of transport
| Distance to Landfill | km | 250 | This will affect the cost of transport
| Contractor Allowance for Margin and Overheads |  | 35%
| Risk/Contingency Allowance |  | 25%
WIND TURBINE DECOMMISSION OUTPUTS
| DESCRIPTION | UNIT | AMOUNT | COMMENT
Yes | Total Cost Exc Recovery | $ | 19462041.5812
| Recovery of Material | $ | 16457770.5
| Total Cost After Recovery | $ | 3004271.0812
| Cost Per MW Exc Recovery | $/MW | 72081.6355
| Cost Per MW Inc Recovery | $/MW | 11126.9299
| Cost Per Turbine Exc Recovery | $/turbine | 259493.8877
| Cost Per Turbine Inc Recovery | $/turbine | 40056.9477

## ASSUMPTIONS 1
DECOMMISSIONING OF WIND TURBINE DIRECT JOB COST
ITEM NO | DESCRIPTION | CREW | UNIT | QUANTITY | RATE PER UNIT | PRODUCTIVITY PER UNIT | DURATION (DAYS) | TOTAL AMOUNT ($) | COMMENT | NO CREWS | NO MEN IN A CREW | TOTAL MEN
1 | Electrical Works | Electrical Works Total | each | 75 | 1640 | 4 | 19 | 31160 | Assumed 4 Turbines Per Day- Isolate each Turbine | 1 | 2 | 2
2 | Removal of Liquid | Fluid Removal Total | lt | 3420000 | 5850 | 75000 | 46 | 269100 | PR to be confirmed | 1 | 6 | 6
2 | Cable Removal | Cable Removal Crew | m | 36450 | 3250 | 7500 | 5 | 16250 | Assumed 6 cables in conduit trenches and 3 cables per tower | 1 | 4 | 4
3 | Removal of Turbine/Blades/Tower | Turbine Crew | Each | 75 | 13780 | 0.5 | 150 | 2067000 | Remove Turbine & Blades 2 days to disassemble | 2 | 8 | 16
|  | Turbine Crew | Each | 75 | 13780 | 1 | 75 | 1033500 | Disassemble Tower 1 tower per day
|  | Internal Mob/Demob | Each | 74 | 12500 | 1 |  | 925000 | Internal relocation, prestart, travel, inefficiency
4 | Removal of Turbine Concrete Footing | Concrete Crew Total | m3 | 0 | 6550 | 25 | 0 | 0 | Assumed only 1m to be removed. Assumed 25m3 per hr demolition | 1 | 2 | 2
|  | Concrete Disposal Crew | tonne | 0 | 11150 | 100 | 0 | 0
|  | Disposal Fee | tonne | 0 | 40 |  |  | 0
|  | Recovery Steel | tonne | 0 | -20 |  |  |  | Steel Recovery . It is assumed that the density of reo is 220kg/m3
|  | Backfill Crew | m3 | 0 | 7750 | 200 | 0 | 0 | Site won material - from onsite borrow pit - maybe reused access road material | 1 | 1 | 1
5 | Removal Of Conduits/Cables | Conduit Crew Total | m | 0 | 8400 | 20 | 0 | 0 | 8 conduits removed & Backfilled 20m Per hr | 2 | 2 | 4 | 0.7725
|  | Pit Crew Total | Each | 0 | 8550 | 1 | 0 | 0 | Assume Concrete pit @ 250m cts - 900x900 pit | 1 | 2 | 2
|  | Conduit Disposal - T&D | m | 0 | 1750 | 250 | 0 | 0 | One T&D can carry 750m of used conduit. Considering the distance total cycle time is around 8hr
|  | Disposal Fee - conduits | tonne | 0 | 65 |  |  | 0 | The weight of 50mm conduit per m is around 0.78kg and it is assumed that there 4 conduits to be removed
|  | Disposal Fee -pits | tonne | 0 | 40 |  |  | 0 | The weight of 63mm conduit per m is around 1.2kg. Disposal rate to be confirmed
6 | Removal of Access Road | Road/Crane Pad Crew | m2 | 0 | 9850 | 120 | 0 | 0 | Assumed cables are by the road and 5m wide | 3 | 1 | 3
|  | Road Material Disposal | m3 | 0 | 18150 | 30 | 0 | 0 | Assumed road formation assumed 150mm recovered and topdressed | 2 | 1 | 2
|  | Disposal Fee | tonne | 0 | 60 |  |  | 0
7 | Removal of Buildings | Building Crew | Each | 1 | 11250 | 20 | 20 | 225000 | Assumed 50 tonne debris per building and in total 3 buildings. One admin, two electrical | 1 | 4 | 4
|  | Concrete Disposal Crew | tonne | 150 | 11150 | 100 | 2 | 22300 |  | 1 | 1 | 1
|  | Disposal Fee | tonne | 150 | 300 |  |  | 45000
8 | Break Down Tower & Turbine | Breakdown Crew | tonne | 60750 | 13090 | 1619.34 | 37.5153 | 491075.0676 | Breakdown the Tower to 26tonne loads. Productivity is cutting two towers per day. It is assumed that tower weight is 5.91 tonne per m | 1 | 6 | 6
|  | Breakdown Crew | tonne | 17070 | 13090 | 1250 | 13.656 | 178757.04 | Breakdown turbine to 26 tone loads
8 | Transport Turbine Material Off Site | Turbine Material Disposal | tonne | 77820 | 175 | 7.3533 | 22009.0923 | 3851591.1538 | For one truck
|  | Disposal Fee | tonne | 77820 | 0 |  |  | 0 | Refer Below
9 | Topsoiling | Topsoil Crew | m2 | 25750 | 6550 | 150 | 18 | 117900 | Assumed for removed access road, removed buildings and removed turbines
10 | Hydroseeding |  | m2 | 25750 | 3 |  |  | 77250
11 | Mobilisation | Plant & Equipment | Each | 14 | 15000 |  |  | 210000 | Assumed 4xExc, 2xRoller, 4xTipper, 1xGrader,3xWatercart
|  | Personnel | Each | 53 | 2100 |  |  | 111300 | Total number of labour to be mobilised, not all of them will be on the site at the same time. Assumed that 10 hours mob, 10 hours demob and 8 hour induction
|  | Mobile 500T | Each | 0 | 100000 |  | 2 | 0
|  | Mobile 200T | Each | 0 | 45000 |  | 2 | 0
|  | Mobile 150T | Each | 2 | 30000 |  | 2 | 120000 |  |  |  | 53
12 | Landfill Disposal |  | tonne |  | 300 |  |  | 0
TOTAL DIRECT JOB COST | [7 empty] | 9792183.2615
DECOMMSSIONING OF WIND TURBINE INDIRECT JOB COST
ITEM NO | DESCRIPTION | UNIT | QUANTITY | RATE |  |  |  | AMOUNT | COMMENT
1 | Establishment of Envrionmental Protection | m | 90000 | 7.5 |  |  |  | 675000
2 | Maintenance of Environmental Protection | week | 45 | 1500 |  |  |  | 67500 | Duration is assumed to be around 45weeks
3 | Construction of Site Office Establishment | LS | 1 | 200000 |  |  |  | 200000
3 | Construction of Site Office Demob | LS | 0.33 | 200000 |  |  |  | 66000
3 | Construction of Site Office recurring cost | week | 45 | 15000 |  |  |  | 675000 | 10000 recurring costs
4 | Traffic Management | LS | 0.5% | 11475683.2615 |  |  |  | 57378.4163 | 0.5% of Base Estimate
TOTAL INDIRECT JOB COST | [7 empty] | 1740878.4163
[7 empty] | Subtotal | 11533061.6778
[7 empty] | Uplift Margin & Overheads | 4036571.5872
15569633.265
[7 empty] | Risk Allowance/Contingency | 3892408.3162
19462041.5812
[7 empty] | Price per Tower | 259493.8877
| RECOVERY OF MATERIALS |  | UNIT | QUANTITY | RATE |  | Recover | AMOUNT | [5 empty] | Material type | Proportion of turbine mass | Assumed pathway is to^^: | Estimated recovery rate | Illustrative scrap value ($/tonne) ## | Estimated recovery as a % of turbine mass
| Cables (Copper and Alloy) | based on 2,298kgs/km | tonne | 550.6821 | 5000 |  | 1 | 2753410.5 | [5 empty] | Steel and iron materials | 88% | Scrap metal facility | 98% | 100 | 86.2%
| Steel |  | tonne | 129231.6 | 100 |  | 1 | 12923160 | [5 empty] | Aluminium and alloys | 1% | Scrap metal facility | 98% | 1000 | 1%
| Aluminium and Alloys |  | tonne | 778.2 | 1000 |  | 1 | 778200 | [5 empty] | Copper and alloys | 0.6% | Scrap metal facility | 98% | 5000 | 0.6%
| Liquids | Recover - Nil Cost - 700kg/m3 | tonne | 2394 | 0 |  | 1 | 0 | [5 empty] | Polymer materials | 4% | Landfill | N/A | N/A | N/A
| Concrete materials | – scrap value is $20/tonne | tonne | 150 | 20 |  | 1 | 3000 | [5 empty] | Carbon / glass composites | 5% | Landfill | N/A | N/A | N/A
| Polymer Material | Landfill | tonne | 3112.8 | 0 |  | 1 | 0 | [5 empty] | Electronics / electrics | 0.6% | Landfill | N/A | N/A | N/A
| Electronics | Landfill | tonne | 466.92 | 0 |  | 1 | 0 | [5 empty] | Fuels and fluids | 0.6% | Landfill | N/A | N/A | N/A
| Carbon/ Glass Composites | Landfill | tonne | 3891 | 0 |  | 1 | 0 | [5 empty] | Not specified | 0.2% | Landfill | N/A | N/A | N/A
| ^^ for material sent to landfill, assume a landfill disposal cost of $300/tonne | [12 empty] | Overall | 100% |  |  | Weighted average = $125/tonne | 87.8%
| ## assumed scrap values are likely to be conservative | [5 empty] | Total Recovery | 16457770.5 | [5 empty] | ^^ for material sent to landfill, assume a landfill disposal cost of $300/tonne
| ** for the concrete foundations, assume all material is sent to a recovery facility – scrap value is $20/tonne | [12 empty] | ## assumed scrap values are likely to be conservative
** for the concrete foundations, assume all material is sent to a recovery facility – scrap value is $20/tonne
[7 empty] | Total | 3004271.0812
[7 empty] | per Tower | 40056.9477

## ASSUMPTIONS 2
LABOUR RATES USED | [5 empty] | CREW RATES PER DAY
DESCRIPTION | UNIT | RATE | COMMENT |  |  | DESCRIPTION | INCLUSION | UNIT | QTY | RATE | TOTAL RATE PER DAY | COMMENT
LAB-CW2 | HR | 65 | General Labour |  |  | Electrical Works | LAB-CW5 | hr | 20 | 82 | 1640 | 2 man crew
LAB-CW3 |  | 75 | Fitter |  |  | Electrical Works Total |  |  |  |  | 1640
LAB-CW5 |  | 82 | Qualified Trade
LAB-CW6 |  | 86 | Operator |  |  | Liquid Waste removal | Liquid Waste Specialist | hr | 10 | 110 | 1100
Liquid Waste Specialist |  | 110 | Liquid Waste Specialist |  |  | Fitter | LAB-CW3 | hr | 40 | 75 | 3000 | 4 man crew
[6 empty] | Labour | LAB-CW2 | hr | 20 | 65 | 1300 | 2 man crew
Hours Per Day | hr | 10 |  |  |  | Tools | Small Tools | hr | 30 | 15 | 450
[6 empty] | Fluid Removal Total |  |  |  |  | 5850
PLANT RATES USED | [5 empty] | Excavator | Excavator 30T | hr | 10 | 175 | 1750
DESCRIPTION | UNIT | RATE | COMMENT |  |  | Concrete Breaker | Hammer 30T | hr | 10 | 20 | 200
Excavator 30T | hr | 175 |  |  |  | Tipper | Tipper 20T | hr | 20 | 150 | 3000 | Taking the concrete to site stockpile
Excavator 20T | hr | 160 |  |  |  | Labour | LAB-CW2 | hr | 20 | 65 | 1300 | 2man crew
Hammer 30T | day | 200 |  |  |  | Tools | Small Tools | hr | 20 | 15 | 300
Hammer 20T | day | 150 |  |  |  | Concrete Crew Total |  |  |  |  | 6550
Tipper 20T | hr | 150
Roller 15-20T | hr | 120 |  |  |  | Excavator | Excavator 20T | hr | 10 | 160 | 1600
Watercart 12-15KL | hr | 130 |  |  |  | Tipper | Tipper 20T | hr | 20 | 150 | 3000 | Taking the concrete to site stockpile
Grader 140 | hr | 210 |  |  |  | Labour | LAB-CW2 | hr | 20 | 65 | 1300 | 2man crew
Small Tools | hr | 15 |  |  |  | Roller | Roller 15-20T | hr | 10 | 120 | 1200
Mobile 500T | hr | 2000 |  |  |  | Watercart | Watercart 12-15KL | hr | 10 | 130 | 1300
Mobile 300T | hr | 1100
Mobile 200T | hr | 850 |  |  |  | Conduit Crew Total |  |  |  |  | 8400
Mobile 150T | hr | 750
Boom lift 40m | day | 480 |  |  |  | Excavator | Excavator 20T | hr | 10 | 160 | 1600
T&D | hr | 175 |  |  |  | Tipper | Tipper 20T | hr | 20 | 150 | 3000 | Taking the concrete to site stockpile
Road Train/Semi Trailer | hr | 200 |  |  |  | Grader | Grader 140 | hr | 10 | 210 | 2100
Oxy Cutter | hr | 12 |  |  |  | Roller | Roller 15-20T | hr | 10 | 120 | 1200
[6 empty] | Watercart | Watercart 12-15KL | hr | 10 | 130 | 1300
NO TRUCKS CONCRETE DISPOSAL | [5 empty] | Labour | LAB-CW2 | hr | 10 | 65 | 650
Distance | km | 200 |  |  |  | Road/Crane Pad Crew |  |  |  |  | 9850
Speed | km/hr | 80
T&D Capacity | tonne | 30 |  |  |  | Excavator | Excavator 30T | hr | 10 | 175 | 1750 | One excavator breaking, one excavator loading
Concrete Loading PR | m3/hr | 10 |  |  |  | Excavator | Excavator 30T | hr | 10 | 175 | 1750
Loading Time | min | 100 |  |  |  | Concrete Breaker | Hammer 30T | hr | 10 | 200 | 2000
Haulage Time | min | 300 |  |  |  | Tipper | Tipper 20T | hr | 20 | 150 | 3000
Unloading | min | 15 |  |  |  | Labour | LAB-CW2 | hr | 40 | 65 | 2600 | 4man crew
Change Trucks | min | 1.2 |  |  |  | Tools | Small Tools | hr | 10 | 15 | 150
Total Cycle Time | min | 416.2 |  |  |  | Building Crew |  |  |  |  | 11250
Number of Trucks | each | 5
|  |  |  | mass | height | Main Crane | Mobile 500T | hr | 10 | 2000 | 20000 | Rates to be confirmed
|  |  |  | 0 | 1 | Main Crane | Mobile 300T | hr | 0 | 1100 | 0 | Rates to be confirmed
NO TRUCKS ROAD MATERIAL DISPOSAL |  |  |  | 1 | 0 | Support Crane | Mobile 150T | hr | 10 | 750 | 7500 | Rates to be confirmed
Distance | km | 250 |  |  |  | Lift | Boom Lift 40m | day | 10 | 48 | 480
Speed | km/hr | 80 |  |  |  | Rigger | LAB-CW3 | hr | 60 | 75 | 4500 | 6man crew
T&D Capacity | tonne | 30 |  |  |  | Labour | LAB-CW2 | hr | 20 | 65 | 1300 | 2man crew
Loading PR | m3/hr | 20 |  |  |  | Turbine Crew |  |  |  |  | 13780
Loading Time | min | 50
Haulage Time | min | 375 |  |  |  | Truck | T&D | hr | 50 | 175 | 8750
Unloading | min | 15 |  |  |  | Excavator | Excavator 30T | hr | 10 | 175 | 1750 | Per day PR is 30x10=300m3. Hence one excavator can load up to 750tonne/30 = 25 trucks
Change Trucks | min | 1.2 |  |  |  | Labour | LAB-CW2 | hr | 10 | 65 | 650
Total Cycle Time | min | 441.2 |  |  |  | Concrete Disposal Crew |  |  |  |  | 11150
Number of Trucks | each | 9
[6 empty] | Truck | T&D | hr | 90 | 175 | 15750
[6 empty] | Excavator | Excavator 30T | hr | 10 | 175 | 1750 | Per day PR is 75*10=750m3 per day. Hence one excavator can load up to 1350tonne/30 = 45 T&D
Recovery of Materials | Yes |  |  |  |  | Labour | LAB-CW2 | hr | 10 | 65 | 650
| No |  |  |  |  | Road Material Disposal |  |  |  |  | 18150
[6 empty] | Crane | Mobile 150T | hr | 20 | 750 | 15000
[6 empty] | Truck | Road Train/Semi Trailer | hr | 170 | 200 | 34000 | Assumed that tower will be transported in 4 pieces, generator will be transported in 10 pieces and blades in 3 pieces. Hence, there will be 17 truck loads for one turbine
[6 empty] | Rigger | LAB-CW3 | hr | 40 | 75 | 3000
[6 empty] | Labour | LAB-CW2 | hr | 10 | 65 | 650
[6 empty] | Turbine Material Disposal |  |  |  |  | 52650
[6 empty] | Excavator | Excavator 20T | hr | 10 | 160 | 1600
[6 empty] | Tipper | Tipper 20T | hr | 20 | 150 | 3000
[6 empty] | Watecart | Watercart 12-15KL | hr | 10 | 130 | 1300
[6 empty] | Labour | LAB-CW2 | hr | 10 | 65 | 650
[6 empty] | Topsoil Crew |  |  |  |  | 6550
[6 empty] | Fitter | LAB-CW3 | hr | 20 | 75 | 1500 | 2man crew
[6 empty] | Labour | LAB-CW2 | hr | 20 | 65 | 1300 | 2man crew
[6 empty] | Tools | Small Tools | hr | 30 | 15 | 450
[6 empty] | Cable Removal Crew |  |  |  |  | 3250
[6 empty] | Excavator | Excavator 20T | hr | 10 | 160 | 1600
[6 empty] | Tipper | Tipper 20T | hr | 20 | 150 | 3000
[6 empty] | Roller | Roller 15-20T | hr | 10 | 120 | 1200
[6 empty] | Watercart | Watercart 12-15KL | hr | 10 | 130 | 1300
[6 empty] | Labour | LAB-CW2 | hr | 10 | 65 | 650 | 1 man crew
[6 empty] | Backfill Crew |  |  |  |  | 7750
[6 empty] | Excavator | Excavator 20T | hr | 10 | 160 | 1600
[6 empty] | Hammer | Hammer 20T | hr | 10 | 15 | 150
[6 empty] | Tipper | Tipper 20T | hr | 20 | 150 | 3000
[6 empty] | Labour | LAB-CW2 | hr | 20 | 65 | 1300
[6 empty] | Roller | Roller 15-20T | hr | 10 | 120 | 1200
[6 empty] | Watercart | Watercart 12-15KL | hr | 10 | 130 | 1300
[6 empty] | Pit Crew Total |  |  |  |  | 8550
[6 empty] | Crane | Mobile 150T | hr | 10 | 750 | 7500
[6 empty] | Lift | Boom Lift 40m | day | 10 | 48 | 480
[6 empty] | Rigger | LAB-CW3 | hr | 40 | 75 | 3000 | 4man crew
[6 empty] | Labour | LAB-CW2 | hr | 20 | 65 | 1300 | 2man crew
[6 empty] | Oxy Cutter | Oxy Cutter | hr | 30 | 12 | 360
[6 empty] | Small Tools | Small Tools | hr | 30 | 15 | 450
[6 empty] | Breakdown Crew |  |  |  |  | 13090